## Tracking Report
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
| Trần Trung Việt - HE153481 | [6 empty] | Vũ Hoàng Anh - HE163109
# | Screen/Function | Feature | Level | In Charge | Status | Actual | # | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Home page | Common | Medium | VietTTHE153481 | Done | iter1 | 1 | Change password | Common | Simple | AnhVHHE163109 | Done | iter1
2 | Show products | Makerting | Medium | VietTTHE153481 | Done | iter1 | 2 | Register for seller | Common | Simple | AnhVHHE163109 | Done | iter1
3 | List of Blogs | Common | Simple | VietTTHE153481 | Done | iter2 | 3 | View Order | Makerting | Simple | AnhVHHE163109 | Done | iter2
4 | Comment blogs | Common | Simple | VietTTHE153481 | Done | iter2 | 4 | Order Detail | Makerting | Simple | AnhVHHE163109 | Done | iter2
5 | Search product | Makerting | Simple | VietTTHE153481 | Done | iter3 | 5 | Cancel Order | Makerting | Simple | AnhVHHE163109 | Done | iter3
6 | Report Shop | Common | Simple | VietTTHE153481 | Done | iter3 | 6 | View Shop | Common | Medium | AnhVHHE163109 | Done | iter3
7 | Favorite Products | Common | Simple | VietTTHE153481 | Done | iter4 | 7 | Search Shop | Admin | Simple | AnhVHHE163109 | Done | iter4
8 | Search Account | Admin | Simple | VietTTHE153481 | Done | iter4 | 8 | Feedback list | Seller | Simple | AnhVHHE163109 | Done | iter4
9 | Manage Blogs | Seller | Medium | VietTTHE153481 | Done | iter4 | 9 | Manage Blog Detail | Seller | Medium | AnhVHHE163109 | Done | iter4
| Nguyễn Trung Hiếu - HE160326 | [6 empty] | Trần Công Minh - HE161354
# | Screen/Function | Feature | Level | In Charge | Status | Actual | # | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Register | Common | Simple | HieuNTHE160326 | Done | iter1 | 1 | Login | Common | Simple | MinhTCHE161354 | Done | iter1
2 | User Profile | Common | Simple | HieuNTHE160326 | Done | iter1 | 2 | Add Address | Common | Simple | MinhTCHE161354 | Done | iter1
3 | Update Profile | Common | Simple | HieuNTHE160326 | Done | iter2 | 3 | View Cart | Marketing | Simple | MinhTCHE161354 | Done | iter2
4 | Blog Detail | Common | Simple | HieuNTHE160326 | Done | iter2 | 4 | Add to cart | Marketing | Simple | MinhTCHE161354 | Done | iter2
5 | Search Blog | Common | Simple | HieuNTHE160326 | Done | iter3 | 5 | Admin Dashboard | Admin | Simple | MinhTCHE161354 | Done | iter3
6 | View Service | Common | Simple | HieuNTHE160326 | Done | iter3 | 6 | List of Accounts | Admin | Simple | MinhTCHE161354 | Done | iter3
7 | Search Service | Common | Simple | HieuNTHE160326 | Done | iter4 | 7 | Account Detail | Admin | Simple | MinhTCHE161354 | Done | iter4
8 | Add feedback | Marketing | Medium | HieuNTHE160326 | Done | iter4 | 8 | Manage Order | Seller | Medium | MinhTCHE161354 | Done | iter4
9 | Seller Dashboard | Seller | Medium | HieuNTHE160326 | Done | iter4 | 9 | Chat with seller | Common | Medium | MinhTCHE161354 | Done | iter4
Lê Sỹ Thái - HE160614
# | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Forgot Password | Common | Medium | ThaiLSHE160614 | Done | iter1
2 | Product Detail | Common | Simple | ThaiLSHE160614 | Done | iter1
3 | Create Order | Marketing | Simple | ThaiLSHE160614 | Done | iter2
4 | List of Report | Admin | Simple | ThaiLSHE160614 | Done | iter2
5 | Product History | Common | Simple | ThaiLSHE160614 | Done | iter3
6 | List of Shops | Admin | Simple | ThaiLSHE160614 | Done | iter3
7 | Shop Information | Admin | Simple | ThaiLSHE160614 | Done | iter4
8 | Manage Products | Seller | Medium | ThaiLSHE160614 | Done | iter4
9 | Reply Feedback | Seller | Simple | ThaiLSHE160614 | Done | iter4