## Tracking Report
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Level | In Charge | Status | Actual | # | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Home page | Common | Medium | VietTTHE153481 | Done | iter1 | 1 | Change password | Common | Simple | AnhVHHE163109 | Done | iter1
2 | Show products | Makerting | Medium | VietTTHE153481 | Done | iter1 | 2 | Register for seller | Common | Simple | AnhVHHE163109 | Done | iter1
3 | Blog list | Common | Simple | VietTTHE153481 | Done | iter2 | 3 | View Order | Makerting | Simple | AnhVHHE163109 | Done | iter2
4 | Manage requests | Admin | Simple | VietTTHE153481 | Doing | iter2 | 4 | Order Detail | Makerting | Simple | AnhVHHE163109 | Done | iter2
5 | Search product | Makerting | Simple | VietTTHE153481 | Done | iter3 | 5 | Cancel Order | Makerting | Simple | AnhVHHE163109 | Doing | iter3
6 | Admin Dashboard | Admin | Simple | VietTTHE153481 | Doing | iter3 | 6 | View Shop | Common | Medium | AnhVHHE163109 | Doing | iter3
7 | Notification | Common | Medium | VietTTHE153481 | Doing | iter4 | 7 | Search Shop | Admin | Simple | AnhVHHE163109 | Done | iter4
8 | Search Account | Admin | Simple | VietTTHE153481 | Done | iter4 | 8 | Reply Feedback | Seller | Medium | AnhVHHE163109 | Doing | iter4
9 | Manage Blogs | Seller | Medium | VietTTHE153481 | Done | iter4 | 9 | Contact Us | Admin | Medium | AnhVHHE163109 | Doing | iter4
# | Screen/Function | Feature | Level | In Charge | Status | Actual | # | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Register | Common | Simple | HieuNTHE160326 | Done | iter1 | 1 | Login | Common | Simple | MinhTCHE161354 | Done | iter1
2 | User Profile | Common | Simple | HieuNTHE160326 | Done | iter1 | 2 | Add Address | Common | Simple | MinhTCHE161354 | Doing | iter1
3 | Update Profile | Common | Simple | HieuNTHE160326 | Done | iter2 | 3 | View Cart | Marketing | Medium | MinhTCHE161354 | Done | iter2
4 | Blog Detail | Common | Simple | HieuNTHE160326 | Done | iter2 | 4 | Create Order | Marketing | Simple | MinhTCHE161354 | Doing | iter2
5 | Search Blog | Common | Simple | HieuNTHE160326 | Done | iter3 | 5 | List Account | Admin | Simple | MinhTCHE161354 | Done | iter3
6 | View Service | Common | Simple | HieuNTHE160326 | Done | iter3 | 6 | Account Detail | Admin | Simple | MinhTCHE161354 | Done | iter3
7 | Search Service | Common | Simple | HieuNTHE160326 | Done | iter4 | 7 | Manage Order | Seller | Medium | MinhTCHE161354 | Doing | iter4
8 | Add feedback | Marketing | Medium | HieuNTHE160326 | Doing | iter4 | 8 | Manage Service | Admin | Medium | MinhTCHE161354 | Doing | iter4
9 | Seller Dashboard | Seller | Medium | HieuNTHE160326 | Doing | iter4 | 9 | Chat with seller | Common | Medium | MinhTCHE161354 | Doing | iter4
# | Screen/Function | Feature | Level | In Charge | Status | Actual
1 | Forgot Password | Common | Medium | ThaiLSHE160614 | Done | iter1
2 | Product Detail | Common | Simple | ThaiLSHE160614 | Done | iter1
3 | Add to cart | Marketing | Medium | ThaiLSHE160614 | Done | iter2
4 | Delete Product in Cart | Marketing | Simple | ThaiLSHE160614 | Done | iter2
5 | Service Detail | Common | Simple | ThaiLSHE160614 | Doing | iter3
6 | List Shop | Admin | Simple | ThaiLSHE160614 | Done | iter3
7 | Shop Details | Admin | Simple | ThaiLSHE160614 | Doing | iter4
8 | Manage Product | Seller | Medium | ThaiLSHE160614 | Doing | iter4
9 | Manage Feedback | Seller | Medium | ThaiLSHE160614 | Doing | iter4