## Tracking
Total Project Tracking
Information in the columns A-E are filled in the project initiation; columns F-J to be filled by the end of each development iteration
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual
1 | Home page | Public | User | Show HomePage: Title, post information includes its thumbnail, brief-info, product information includes its thumbnail, title, brief information | VietTTHE153481 | Done | iter1
2 | Show products | Makerting | User | Display product list, product category | VietTTHE153481 | Done | iter1
3 | Blog list | Public | Admin | Show the posts paginatedly (sorted by updated date) + the right sider with the post search box, post categories, five featured posts (thumbnail, title); Post information includes its thumbnail, title, category, post date, brief-info; the user is redirected to the Blog Details page on his/her clicking on a post, redirected to this Blogs List page if the user clicks on a post category | VietTTHE153481 | Done | iter2
4 | List Account | Admin | Admin | Show list of user's accounts | VietTTHE153481 | Done | iter2
5 | Search product | Makerting | User | Search products by product name, category name, price | VietTTHE153481 | Doing | iter3
6 | Search account | Admin | Admin | Allows admins to find user accounts quickly | VietTTHE153481 | Doing | iter3
7 | Notification | Admin | Admin | The screen is used to display system or administrator messages to the user | VietTTHE153481 | To Do | iter4
8 | Update account role | Common | Admin | Allow admin to update user account role | VietTTHE153481 | To Do | iter4
9 | Manage Blogs | Seller | Seller | Screen that allows sellers to add, edit and delete Blogs | VietTTHE153481 | To Do | iter4